## HOME
FAIR CRM PROJECT HUB
Current Version | v0.1.8 | Area | Progress
Project Mode | Product Development | Backend | 70%
Backend | FastAPI + SQLAlchemy + MySQL/MariaDB | Frontend | 10%
Frontend | React / Turkish UI target | Import | 20%
Documentation Source | FAIR_CRM_PROJECT.xlsx | Scraper | 0%
Root MD Files | README.md / MASTER_CONTEXT.md / CHANGELOG.md
Next Goal | v0.1.8 Smart Import Engine preparation
Last Updated | 2026-06-30
Tables | 13
API Endpoints | 39
Single Source of Truth Rule: Roadmap, Database, API, Business Rules, Tests, Bugs, Ideas and Decisions live in this workbook.

## Roadmap
Version | Feature | Status | Notes
v0 | Foundation | Done | Base backend, models, CRUD foundation
v0.1 | Usable CRM | Done | Dashboard, customer profiles, seed data, health_check and dev_check READY
v0.2 | Auth Foundation | In Progress | SaaS-ready organization concept, email login, JWT, RBAC and user roles
v0.3 | Customer Management | Planned | Customer/contact CRUD improvements, search, filter and profile timeline
v0.4 | Fair & Participation Management | Planned | Fair CRUD, participation history and customer-fair relationships
v0.5 | Smart Import Engine | Planned | Import preview, validation, duplicate detection and merge decision
v0.6 | Scraper Framework | Planned | Adapter-based fair website scraper framework
v0.7 | Dashboard & Reports | Planned | KPIs, recent activity and fair/customer analytics
v0.8 | Communication | Planned | WhatsApp/e-mail history and communication workflows
v1.0 | Commercial Release | Planned | Production-ready SaaS release candidate

## Sprint
Priority | Task | Status | Version/Target
High | Standardize project structure | Done | v0.1.4
High | Keep README / MASTER_CONTEXT / CHANGELOG only as root MDs | Done | v0.1.4
High | Use FAIR_CRM_PROJECT.xlsx as project hub | Done | v0.1.4
High | Test /dashboard/summary | Next | v0.1
High | Test /customers/{id}/profile | Next | v0.1
Medium | Add pagination defaults to list endpoints | Planned | v0.1
Medium | Add global search endpoint | Planned | v0.1
High | Build Smart Import preview endpoint | Planned | v0.2

## Database
Table | Model Class | Description | Status
users | User | Supporting table | Active
customers | Customer | Core CRM table | Active
contacts | Contact | Core CRM table | Active
customer_phones | CustomerPhone | Supporting table | Active
customer_emails | CustomerEmail | Supporting table | Active
notes | Note | Supporting table | Active
fairs | Fair | Core CRM table | Active
fair_participations | FairParticipation | Core CRM table | Active
import_batches | ImportBatch | Supporting table | Active
import_rows | ImportRow | Supporting table | Active
scraper_sources | ScraperSource | Supporting table | Active
scraper_runs | ScraperRun | Supporting table | Active
audit_logs | AuditLog | Supporting table | Active

## Columns
Table | Column | Type | Nullable | PK | Unique | Index | Description | Used In
users | id | Integer | No | Yes | No | Yes | Primary key. Sistem içi benzersiz kayıt ID. | CRM / API
users | full_name | String(150) | No | No | No | No | Kişi veya kullanıcı tam adı. | CRM / API
users | email | String(150) | No | No | Yes | No | E-posta adresi. | CRM / API
users | password_hash | String(255) | No | No | No | No | users.password_hash alanı. | CRM / API
users | role | String(50) | No | No | No | No | users.role alanı. | CRM / API
users | is_active | Boolean | No | No | No | No | Kayıt aktif/pasif durumu. | CRM / API
users | created_at | DateTime | No | No | No | No | Kayıt oluşturulma tarihi. | CRM / API
users | updated_at | DateTime | No | No | No | No | Son güncelleme tarihi. | CRM / API
customers | id | Integer | No | Yes | No | Yes | Primary key. Sistem içi benzersiz kayıt ID. | CRM / API
customers | company_name | String(255) | No | No | No | Maybe | Kullanıcının gördüğü gerçek firma adı. | CRM / API
customers | normalized_company_name | String(255) | Yes | No | No | Maybe | Arama ve duplicate detection için normalize edilmiş firma adı. | CRM / API / Import
customers | website | String(255) | Yes | No | No | Maybe | Firma web sitesi. | CRM / API
customers | normalized_website | String(255) | Yes | No | No | Maybe | Arama/eşleştirme için normalize edilmiş web sitesi. | CRM / API / Import
customers | main_phone | String(50) | Yes | No | No | Maybe | Firmanın ana telefonu. | CRM / API
customers | normalized_main_phone | String(50) | Yes | No | No | Maybe | Eşleştirme için normalize edilmiş ana telefon. | CRM / API / Import
customers | tax_number | String(50) | Yes | No | No | Maybe | Vergi numarası; duplicate detection için yardımcı alan. | CRM / API
customers | tax_office | String(100) | Yes | No | No | No | Vergi dairesi. | CRM / API
customers | country | String(100) | Yes | No | No | No | Ülke bilgisi. | CRM / API
customers | city | String(100) | Yes | No | No | No | Şehir bilgisi. | CRM / API
customers | district | String(100) | Yes | No | No | No | İlçe bilgisi. | CRM / API
customers | address | Text | Yes | No | No | No | Adres bilgisi. | CRM / API
customers | description | Text | Yes | No | No | No | Genel açıklama. | CRM / API
customers | source | String(30) | No | No | No | No | Kaydın kaynağı: manual/import/scraper vb. | CRM / API
customers | is_active | Boolean | No | No | No | No | Kayıt aktif/pasif durumu. | CRM / API
customers | is_deleted | Boolean | No | No | No | No | Soft delete için silindi bilgisi. | CRM / API
customers | created_at | DateTime | No | No | No | No | Kayıt oluşturulma tarihi. | CRM / API
customers | updated_at | DateTime | No | No | No | No | Son güncelleme tarihi. | CRM / API
customers | deleted_at | DateTime | Yes | No | No | No | Soft delete tarihi. | CRM / API
contacts | id | Integer | No | Yes | No | Yes | Primary key. Sistem içi benzersiz kayıt ID. | CRM / API
contacts | customer_id | Integer | No | No | No | Maybe | İlişkili müşteri/firma ID. | CRM / API
contacts | full_name | String(150) | No | No | No | Maybe | Kişi veya kullanıcı tam adı. | CRM / API
contacts | normalized_full_name | String(150) | Yes | No | No | Maybe | contacts.normalized_full_name alanı. | CRM / API / Import
contacts | title | String(100) | Yes | No | No | No | Başlık. | CRM / API
contacts | department | String(100) | Yes | No | No | No | Departman bilgisi. | CRM / API
contacts | phone | String(50) | Yes | No | No | No | Telefon numarası. | CRM / API
contacts | email | String(150) | Yes | No | No | No | E-posta adresi. | CRM / API
contacts | note | Text | Yes | No | No | No | Not içeriği. | CRM / API
contacts | is_primary | Boolean | No | No | No | No | Birincil iletişim alanı mı? | CRM / API
contacts | is_deleted | Boolean | No | No | No | No | Soft delete için silindi bilgisi. | CRM / API
contacts | created_at | DateTime | No | No | No | No | Kayıt oluşturulma tarihi. | CRM / API
contacts | updated_at | DateTime | No | No | No | No | Son güncelleme tarihi. | CRM / API
contacts | deleted_at | DateTime | Yes | No | No | No | Soft delete tarihi. | CRM / API
customer_phones | id | Integer | No | Yes | No | Yes | Primary key. Sistem içi benzersiz kayıt ID. | CRM / API
customer_phones | customer_id | Integer | No | No | No | Maybe | İlişkili müşteri/firma ID. | CRM / API
customer_phones | contact_id | Integer | Yes | No | No | Maybe | İlişkili kişi ID. | CRM / API
customer_phones | phone_number | String(50) | No | No | No | No | customer_phones.phone_number alanı. | CRM / API
customer_phones | normalized_phone | String(50) | Yes | No | No | Maybe | Normalize edilmiş telefon. | CRM / API / Import
customer_phones | phone_type | String(50) | Yes | No | No | No | customer_phones.phone_type alanı. | CRM / API
customer_phones | label | String(50) | Yes | No | No | No | customer_phones.label alanı. | CRM / API
customer_phones | is_primary | Boolean | No | No | No | No | Birincil iletişim alanı mı? | CRM / API
customer_phones | source | String(30) | No | No | No | No | Kaydın kaynağı: manual/import/scraper vb. | CRM / API
customer_phones | is_deleted | Boolean | No | No | No | No | Soft delete için silindi bilgisi. | CRM / API
customer_phones | created_at | DateTime | No | No | No | No | Kayıt oluşturulma tarihi. | CRM / API
customer_phones | updated_at | DateTime | No | No | No | No | Son güncelleme tarihi. | CRM / API
customer_phones | deleted_at | DateTime | Yes | No | No | No | Soft delete tarihi. | CRM / API
customer_emails | id | Integer | No | Yes | No | Yes | Primary key. Sistem içi benzersiz kayıt ID. | CRM / API
customer_emails | customer_id | Integer | No | No | No | Maybe | İlişkili müşteri/firma ID. | CRM / API
customer_emails | contact_id | Integer | Yes | No | No | Maybe | İlişkili kişi ID. | CRM / API
customer_emails | email | String(150) | No | No | No | No | E-posta adresi. | CRM / API
customer_emails | normalized_email | String(150) | Yes | No | No | Maybe | Normalize edilmiş e-posta. | CRM / API / Import
customer_emails | email_type | String(50) | Yes | No | No | No | customer_emails.email_type alanı. | CRM / API
customer_emails | label | String(50) | Yes | No | No | No | customer_emails.label alanı. | CRM / API
customer_emails | is_primary | Boolean | No | No | No | No | Birincil iletişim alanı mı? | CRM / API
customer_emails | validation_status | String(30) | No | No | No | Maybe | customer_emails.validation_status alanı. | CRM / API
customer_emails | validation_message | String(255) | Yes | No | No | No | customer_emails.validation_message alanı. | CRM / API
customer_emails | source | String(30) | No | No | No | No | Kaydın kaynağı: manual/import/scraper vb. | CRM / API
customer_emails | is_deleted | Boolean | No | No | No | No | Soft delete için silindi bilgisi. | CRM / API
customer_emails | created_at | DateTime | No | No | No | No | Kayıt oluşturulma tarihi. | CRM / API
customer_emails | updated_at | DateTime | No | No | No | No | Son güncelleme tarihi. | CRM / API
customer_emails | deleted_at | DateTime | Yes | No | No | No | Soft delete tarihi. | CRM / API
notes | id | Integer | No | Yes | No | Yes | Primary key. Sistem içi benzersiz kayıt ID. | CRM / API
notes | customer_id | Integer | No | No | No | No | İlişkili müşteri/firma ID. | CRM / API
notes | contact_id | Integer | Yes | No | No | No | İlişkili kişi ID. | CRM / API
notes | fair_id | Integer | Yes | No | No | No | İlişkili fuar ID. | CRM / API
notes | fair_participation_id | Integer | Yes | No | No | No | notes.fair_participation_id alanı. | CRM / API
notes | note_date | DateTime | No | No | No | No | notes.note_date alanı. | CRM / API
notes | detail | Text | No | No | No | No | notes.detail alanı. | CRM / API
notes | note_type | String(50) | Yes | No | No | No | notes.note_type alanı. | CRM / API
notes | created_by_user_id | Integer | Yes | No | No | No | notes.created_by_user_id alanı. | CRM / API
notes | is_deleted | Boolean | No | No | No | No | Soft delete için silindi bilgisi. | CRM / API
notes | created_at | DateTime | No | No | No | No | Kayıt oluşturulma tarihi. | CRM / API
notes | updated_at | DateTime | No | No | No | No | Son güncelleme tarihi. | CRM / API
notes | deleted_at | DateTime | Yes | No | No | No | Soft delete tarihi. | CRM / API
fairs | id | Integer | No | Yes | No | Yes | Primary key. Sistem içi benzersiz kayıt ID. | CRM / API
fairs | fair_name | String(255) | No | No | No | Maybe | Fuar adı. | CRM / API
fairs | normalized_fair_name | String(255) | Yes | No | No | Maybe | fairs.normalized_fair_name alanı. | CRM / API / Import
fairs | organizer | String(255) | Yes | No | No | No | Organizatör bilgisi. | CRM / API
fairs | venue | String(255) | Yes | No | No | No | fairs.venue alanı. | CRM / API
fairs | city | String(100) | Yes | No | No | No | Şehir bilgisi. | CRM / API
fairs | country | String(100) | Yes | No | No | No | Ülke bilgisi. | CRM / API
fairs | start_date | Date | Yes | No | No | Maybe | Başlangıç tarihi. | CRM / API
fairs | end_date | Date | Yes | No | No | Maybe | Bitiş tarihi. | CRM / API
fairs | website | String(255) | Yes | No | No | No | Firma web sitesi. | CRM / API
fairs | is_active | Boolean | No | No | No | No | Kayıt aktif/pasif durumu. | CRM / API
fairs | is_deleted | Boolean | No | No | No | No | Soft delete için silindi bilgisi. | CRM / API
fairs | created_at | DateTime | No | No | No | No | Kayıt oluşturulma tarihi. | CRM / API
fairs | updated_at | DateTime | No | No | No | No | Son güncelleme tarihi. | CRM / API
fairs | deleted_at | DateTime | Yes | No | No | No | Soft delete tarihi. | CRM / API
fair_participations | id | Integer | No | Yes | No | Yes | Primary key. Sistem içi benzersiz kayıt ID. | CRM / API
fair_participations | customer_id | Integer | No | No | No | Maybe | İlişkili müşteri/firma ID. | CRM / API
fair_participations | fair_id | Integer | No | No | No | Maybe | İlişkili fuar ID. | CRM / API
fair_participations | hall | String(100) | Yes | No | No | No | Fuar salonu. | CRM / API
fair_participations | stand_number | String(100) | Yes | No | No | No | fair_participations.stand_number alanı. | CRM / API
fair_participations | exhibitor_profile_url | String(500) | Yes | No | No | No | fair_participations.exhibitor_profile_url alanı. | CRM / API
fair_participations | external_exhibitor_id | String(100) | Yes | No | No | Maybe | fair_participations.external_exhibitor_id alanı. | CRM / API
fair_participations | participation_status | String(50) | No | No | No | No | Katılım durumu. | CRM / API
fair_participations | source | String(30) | No | No | No | No | Kaydın kaynağı: manual/import/scraper vb. | CRM / API
fair_participations | is_deleted | Boolean | No | No | No | No | Soft delete için silindi bilgisi. | CRM / API
fair_participations | created_at | DateTime | No | No | No | No | Kayıt oluşturulma tarihi. | CRM / API
fair_participations | updated_at | DateTime | No | No | No | No | Son güncelleme tarihi. | CRM / API
fair_participations | deleted_at | DateTime | Yes | No | No | No | Soft delete tarihi. | CRM / API
import_batches | id | Integer | No | Yes | No | Yes | Primary key. Sistem içi benzersiz kayıt ID. | CRM / API / Import
import_batches | fair_id | Integer | Yes | No | No | No | İlişkili fuar ID. | CRM / API / Import
import_batches | source_type | String(50) | No | No | No | No | import_batches.source_type alanı. | CRM / API / Import
import_batches | source_name | String(255) | Yes | No | No | No | import_batches.source_name alanı. | CRM / API / Import
import_batches | original_file_name | String(255) | Yes | No | No | No | import_batches.original_file_name alanı. | CRM / API / Import
import_batches | status | String(50) | No | No | No | No | Durum bilgisi. | CRM / API / Import
import_batches | total_rows | Integer | No | No | No | No | Toplam import satır sayısı. | CRM / API / Import
import_batches | successful_rows | Integer | No | No | No | No | import_batches.successful_rows alanı. | CRM / API / Import
import_batches | warning_rows | Integer | No | No | No | No | import_batches.warning_rows alanı. | CRM / API / Import
import_batches | error_rows | Integer | No | No | No | No | import_batches.error_rows alanı. | CRM / API / Import
import_batches | created_by_user_id | Integer | Yes | No | No | No | import_batches.created_by_user_id alanı. | CRM / API / Import
import_batches | created_at | DateTime | No | No | No | No | Kayıt oluşturulma tarihi. | CRM / API / Import
import_batches | updated_at | DateTime | No | No | No | No | Son güncelleme tarihi. | CRM / API / Import
import_rows | id | Integer | No | Yes | No | Yes | Primary key. Sistem içi benzersiz kayıt ID. | CRM / API / Import
import_rows | import_batch_id | Integer | No | No | No | No | İlişkili import batch ID. | CRM / API / Import
import_rows | row_number | Integer | No | No | No | No | Import dosyasındaki satır numarası. | CRM / API / Import
import_rows | raw_data_json | JSONEncodedText | Yes | No | No | No | Import satırının ham verisi. DB tarafında TEXT olarak saklanır, Python tarafında JSON gibi kullanılır. | CRM / API / Import
import_rows | normalized_data_json | JSONEncodedText | Yes | No | No | No | Normalize edilmiş import satırı. | CRM / API / Import
import_rows | detected_customer_id | Integer | Yes | No | No | No | Duplicate detection sonucu bulunan müşteri ID. | CRM / API / Import
import_rows | detected_fair_participation_id | Integer | Yes | No | No | No | Duplicate detection sonucu bulunan katılım ID. | CRM / API / Import
import_rows | match_score | DECIMAL(5, 2) | Yes | No | No | No | Eşleşme güven/benzerlik puanı. | CRM / API / Import
import_rows | detection_status | String(50) | No | No | No | No | Tespit durumu: new/review/duplicate/error vb. | CRM / API / Import
import_rows | decision_status | String(50) | No | No | No | No | Kullanıcı karar durumu: pending/created/merged/ignored vb. | CRM / API / Import
import_rows | decision_payload_json | JSONEncodedText | Yes | No | No | No | Kullanıcının merge/create karar detayları. | CRM / API / Import
import_rows | warning_message | Text | Yes | No | No | No | Import uyarı mesajı. | CRM / API / Import
import_rows | error_message | Text | Yes | No | No | No | Import hata mesajı. | CRM / API / Import
import_rows | created_at | DateTime | No | No | No | No | Kayıt oluşturulma tarihi. | CRM / API / Import
import_rows | updated_at | DateTime | No | No | No | No | Son güncelleme tarihi. | CRM / API / Import
scraper_sources | id | Integer | No | Yes | No | Yes | Primary key. Sistem içi benzersiz kayıt ID. | CRM / API
scraper_sources | fair_id | Integer | Yes | No | No | No | İlişkili fuar ID. | CRM / API
scraper_sources | source_name | String(255) | No | No | No | No | scraper_sources.source_name alanı. | CRM / API
scraper_sources | base_url | String(500) | No | No | No | No | scraper_sources.base_url alanı. | CRM / API
scraper_sources | adapter_name | String(255) | No | No | No | No | scraper_sources.adapter_name alanı. | CRM / API
scraper_sources | is_active | Boolean | No | No | No | No | Kayıt aktif/pasif durumu. | CRM / API
scraper_sources | created_at | DateTime | No | No | No | No | Kayıt oluşturulma tarihi. | CRM / API
scraper_sources | updated_at | DateTime | No | No | No | No | Son güncelleme tarihi. | CRM / API
scraper_runs | id | Integer | No | Yes | No | Yes | Primary key. Sistem içi benzersiz kayıt ID. | CRM / API
scraper_runs | scraper_source_id | Integer | No | No | No | No | scraper_runs.scraper_source_id alanı. | CRM / API
scraper_runs | status | String(50) | No | No | No | No | Durum bilgisi. | CRM / API
scraper_runs | total_found | Integer | No | No | No | No | scraper_runs.total_found alanı. | CRM / API
scraper_runs | output_file_name | String(255) | Yes | No | No | No | scraper_runs.output_file_name alanı. | CRM / API
scraper_runs | error_message | Text | Yes | No | No | No | Import hata mesajı. | CRM / API
scraper_runs | started_at | DateTime | No | No | No | No | scraper_runs.started_at alanı. | CRM / API
scraper_runs | finished_at | DateTime | Yes | No | No | No | scraper_runs.finished_at alanı. | CRM / API
audit_logs | id | Integer | No | Yes | No | Yes | Primary key. Sistem içi benzersiz kayıt ID. | CRM / API
audit_logs | user_id | Integer | Yes | No | No | No | audit_logs.user_id alanı. | CRM / API
audit_logs | entity_type | String(100) | No | No | No | No | audit_logs.entity_type alanı. | CRM / API
audit_logs | entity_id | Integer | No | No | No | No | audit_logs.entity_id alanı. | CRM / API
audit_logs | action | String(50) | No | No | No | No | audit_logs.action alanı. | CRM / API
audit_logs | old_data_json | JSONEncodedText | Yes | No | No | No | audit_logs.old_data_json alanı. | CRM / API
audit_logs | new_data_json | JSONEncodedText | Yes | No | No | No | audit_logs.new_data_json alanı. | CRM / API
audit_logs | created_at | DateTime | No | No | No | No | Kayıt oluşturulma tarihi. | CRM / API

## Relationships
Parent Table | Child Table | Relation | Type
customers | contacts | customers.id -> contacts.customer_id | many-to-one / foreign key
customers | customer_phones | customers.id -> customer_phones.customer_id | many-to-one / foreign key
contacts | customer_phones | contacts.id -> customer_phones.contact_id | many-to-one / foreign key
customers | customer_emails | customers.id -> customer_emails.customer_id | many-to-one / foreign key
contacts | customer_emails | contacts.id -> customer_emails.contact_id | many-to-one / foreign key
customers | notes | customers.id -> notes.customer_id | many-to-one / foreign key
contacts | notes | contacts.id -> notes.contact_id | many-to-one / foreign key
fairs | notes | fairs.id -> notes.fair_id | many-to-one / foreign key
fair_participations | notes | fair_participations.id -> notes.fair_participation_id | many-to-one / foreign key
users | notes | users.id -> notes.created_by_user_id | many-to-one / foreign key
customers | fair_participations | customers.id -> fair_participations.customer_id | many-to-one / foreign key
fairs | fair_participations | fairs.id -> fair_participations.fair_id | many-to-one / foreign key
fairs | import_batches | fairs.id -> import_batches.fair_id | many-to-one / foreign key
users | import_batches | users.id -> import_batches.created_by_user_id | many-to-one / foreign key
import_batches | import_rows | import_batches.id -> import_rows.import_batch_id | many-to-one / foreign key
customers | import_rows | customers.id -> import_rows.detected_customer_id | many-to-one / foreign key
fair_participations | import_rows | fair_participations.id -> import_rows.detected_fair_participation_id | many-to-one / foreign key
fairs | scraper_sources | fairs.id -> scraper_sources.fair_id | many-to-one / foreign key
scraper_sources | scraper_runs | scraper_sources.id -> scraper_runs.scraper_source_id | many-to-one / foreign key
users | audit_logs | users.id -> audit_logs.user_id | many-to-one / foreign key

## API
Method | Endpoint | Tag | Description | Status
GET | / | Root | API status | Done
GET | /health-check | Health | Database connection health | Done
POST | /contacts/ | Contacts | Create contact | Done
GET | /contacts/ | Contacts | List contacts | Done
GET | /contacts/{contact_id} | Contacts | Get contact | Done
PUT | /contacts/{contact_id} | Contacts | Update contact | Done
DELETE | /contacts/{contact_id} | Contacts | Delete contact | Done
POST | /customer-emails/ | Customer Emails | Create customer email | Done
GET | /customer-emails/ | Customer Emails | List customer emails | Done
GET | /customer-emails/{email_id} | Customer Emails | Get customer email | Done
PUT | /customer-emails/{email_id} | Customer Emails | Update customer email | Done
DELETE | /customer-emails/{email_id} | Customer Emails | Delete customer email | Done
POST | /customer-phones/ | Customer Phones | Create customer phone | Done
GET | /customer-phones/ | Customer Phones | List customer phones | Done
GET | /customer-phones/{phone_id} | Customer Phones | Get customer phone | Done
PUT | /customer-phones/{phone_id} | Customer Phones | Update customer phone | Done
DELETE | /customer-phones/{phone_id} | Customer Phones | Delete customer phone | Done
POST | /customers/ | Customers | Create customer | Done
GET | /customers/ | Customers | List customers | Done
GET | /customers/{customer_id}/profile | Customers | Get customer profile | Done
GET | /customers/{customer_id} | Customers | Get customer | Done
PUT | /customers/{customer_id} | Customers | Update customer | Done
DELETE | /customers/{customer_id} | Customers | Delete customer | Done
GET | /dashboard/summary | Dashboard | Get dashboard summary | Done
POST | /fair-participations/ | Fair Participations | Create fair participation | Done
GET | /fair-participations/ | Fair Participations | List fair participations | Done
GET | /fair-participations/{participation_id} | Fair Participations | Get fair participation | Done
PUT | /fair-participations/{participation_id} | Fair Participations | Update fair participation | Done
DELETE | /fair-participations/{participation_id} | Fair Participations | Delete fair participation | Done
POST | /fairs/ | Fairs | Create fair | Done
GET | /fairs/ | Fairs | List fairs | Done
GET | /fairs/{fair_id} | Fairs | Get fair | Done
PUT | /fairs/{fair_id} | Fairs | Update fair | Done
DELETE | /fairs/{fair_id} | Fairs | Delete fair | Done
POST | /notes/ | Notes | Create note | Done
GET | /notes/ | Notes | List notes | Done
GET | /notes/{note_id} | Notes | Get note | Done
PUT | /notes/{note_id} | Notes | Update note | Done
DELETE | /notes/{note_id} | Notes | Delete note | Done

## Business Rules
Rule | Description
Backend language | All backend/database/API names are English.
Frontend language | All user-facing labels and messages should be Turkish.
Architecture preservation | Use the existing FastAPI + SQLAlchemy structure unless a major change is explicitly approved.
Customer matching | Use normalized company names, Turkish character normalization, legal suffix cleanup and fuzzy matching.
Duplicate rule | Same company should not be blindly inserted twice for the same fair.
Merge rule | If incoming import data has missing/new fields, user should decide create/merge/ignore.
Normalized fields | Fields like normalized_company_name are system-generated and not user-editable.
JSON compatibility | JSON-like import fields are stored as TEXT for MySQL/MariaDB compatibility through JSONEncodedText.
Database credentials are never hardcoded | Use backend/.env locally and keep backend/.env out of version control.

## Import Mapping
Source Field | Normalize Step | Target Table | Target Column | Notes
Company / Firma | normalize company name | customers | company_name | Main visible company name
Website / Web | normalize URL | customers | website | Company website
Phone / Telefon | normalize phone | customer_phones | phone_number | Customer-level phone
Email / E-posta | normalize email | customer_emails | email | Customer-level email
Contact Name / Yetkili | trim title/name | contacts | full_name | Contact person
Position / Görev | trim | contacts | title | Contact role
Fair / Fuar | match fair | fairs | fair_name | Fair record
Hall / Salon | trim | fair_participations | hall | Hall info
Stand / Stand No | trim | fair_participations | stand | Stand code
Area / m2 | parse decimal | fair_participations | area_m2 | Stand area

## Seed
Entity | Count | Status
customers | 100 | Loaded
contacts | 200 | Loaded
customer_phones | 200 | Loaded
customer_emails | 200 | Loaded
fairs | 5 | Loaded
fair_participations | 200 | Loaded
notes | 125 | Loaded
import_batches | 1 | Loaded
import_rows | 6 | Loaded

## Tests
Module | Scenario | Status
Backend startup | uvicorn app.main:app --reload | Next
Swagger | Open http://127.0.0.1:8000/docs | Next
Dashboard | GET /dashboard/summary returns counts | Next
Customers | GET /customers returns seeded customers | Next
Customer Profile | GET /customers/1/profile returns related data | Next
Participations | GET /fair-participations returns seeded participations | Next
Seed reset | python seed.py --reset recreates seed data | Done
Health Check | python scripts/health_check.py returns SYSTEM READY | Done

## Bugs
ID | Description | Status
BUG-001 | No open bugs recorded in this workbook yet. | Open/Review

## Decisions
Date | Decision | Reason
2026-06-30 | Use Excel as project hub | Avoid dozens of stale MD files; keep project information in one workbook.
2026-06-30 | Keep only three root MD files | README, MASTER_CONTEXT and CHANGELOG are enough for current stage.
2026-06-30 | Keep docs/ for binary/reference artifacts | ER diagrams, mockups, Postman collections and samples stay in docs/.
2026-06-30 | Add resources/ | Logos, icons, Excel templates, imports and branding resources stay outside docs/.
2026-06-29 | Backend English / Frontend Turkish | International backend standard with Turkish user experience.
2026-06-30 | MySQL/MariaDB JSON fix | Use JSONEncodedText to avoid JSON type incompatibility.
2026-06-30 | Environment-based DB configuration | Database credentials must be stored in backend/.env; backend/.env.example is the safe template committed to the project.
2026-06-30 | Add local health check automation | User needs one command to verify current project state after each change.
2026-06-30 | Design FAIR CRM as future SaaS | Product may be sold to other companies later, so auth and data ownership must be organization-ready.
2026-06-30 | Use organization as tenant concept | Backend/database/API naming stays English and future multi-tenant expansion remains possible.
2026-06-30 | Use email + password authentication | Simple and standard login method; compatible with future Google/Microsoft OAuth.
2026-06-30 | Use JWT access tokens | API authentication starts with access tokens; refresh token support can be added after the first login flow.
2026-06-30 | Use RBAC with permission-ready design | Initial roles are super_admin, admin, manager, sales and viewer; permission tables can be added without redesign.

## Ideas
Idea | Priority | Target
Dashboard recent activity widget | Medium | v0.1
Global search across customers/fairs/contacts | High | v0.1
Import preview diff screen | High | v0.2
Scraper adapter template generator | Medium | v0.3

## Release History
Version | Date | Notes
v0.1.0 | 2026-06-30 | Usable CRM endpoints
v0.1.1 | 2026-06-30 | MySQL/MariaDB JSON compatibility fix
v0.1.2 | 2026-06-30 | Product development standard docs
v0.1.3 | 2026-06-30 | Excel project hub introduced
v0.1.4 | 2026-06-30 | Final simplified project standard applied
v0.1.5 | 2026-06-30 | Environment configuration standardized; .env.example, config module and README setup steps updated.
v0.1.6 | 2026-06-30 | Local health check automation added; validates .env, DB connection, tables, seed counts, app import and key routes.
v0.1.8 | Master Stabilization | Version sync, full health check, import mapping alignment
v0.2.0 | 2026-06-30 | Auth foundation design documented: SaaS-ready organization concept, email/password login, JWT and RBAC direction.